## Sheet1
Phase | Week | CRISP-DM Steps | Resources | Risks | Status | Comments
Milestone 1--Team Information/Communication Plan | Week-1 | Team Formation & Project Plan | Supraja | NA | Completed | Doing it alone, Peer Reviewer identified.
Milestone 2-- Project Identification & Data Understanding | Week-2 | Identify the Problem to solve | Supraja |  | Not Started
| Week-2 | Identify Data Sources and Create Highlevel Data Dictionary | Supraja |  | Not Started
| Week-2 | Document Problem, Objectives, Assumptions, Expected Outputs | Supraja |  | Not Started
| Week-2 | Model Evaluation Criteria Definition | Supraja |  | Not Started
| Week-3 | Deep Dive data and validate the Problem | Supraja |  | Not Started
| Week-3 | Data Preparation | Supraja |  | Not Started
| Week-3 | Peer Review: Review the approach and incoporate feedback if any | Supraja & Victoria Hall |  | Not Started
Milestone 3--Preliminary Analysis | Week-4 | Exploratory Data Analysis | Supraja |  | Not Started
| Week-5 | Build the Model | Supraja |  | Not Started
| Week-6 | Hyperparameter Tuning | Supraja |  | Not Started
| Week-7 | Finalize the Model build | Supraja |  | Not Started
| Week-7 | Model Evaluation | Supraja |  | Not Started
| Week-8 | Peer Review: Review the model outputs and incorporate feedback if any | Supraja & Victoria Hall |  | Not Started
Milestone 4--Project Presentation & Status | Week-9 | Deployment | Supraja |  | Not Started
| Week-10 | Creating final Code files | Supraja |  | Not Started
| Week-11 | Conclusion and Recommendations
| Week-11 | Peer Review: Review the Conclusion and icnorporate feedback if any | Supraja & Victoria Hall |  | Not Started
Milestone 5--Final Project Paper and Presentation | Week-12 | Create final Summary Documents & Presentation | Supraja |  | Not Started